## Master Dashboard
ACME CORPORATION - TEAM TASK PLANNER - MASTER DASHBOARD
Last Updated: | 2025-09-17 06:00
Project/Team | Total Tasks | Completed | In Progress | Pending | Overdue | Team Size | Workload %
Mobile Development | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Science | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI/UX Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Tasks:
Overall Progress:
Critical Issues:
Average Team Load:

## Team Allocation
TEAM RESOURCE ALLOCATION
Employee Name | Team | Role | Current Tasks | Hours/Week | Availability % | Skills | Next Available | Status
John Doe | Mobile Development | Senior Developer | 3 | 40 | 90 | Programming, Analysis | 2024-01-15 | Busy
Jane Smith | Mobile Development | Developer | 2 | 35 | 75 | Design, Development | 2024-01-10 | Available
Team Member 1 | Data Science | Developer | 2 | 40 | 70 | Various Skills | 2024-01-08 | Available
Team Member 2 | Data Science | Senior Developer | 3 | 40 | 85 | Leadership, Technical | 2024-01-12 | Busy
TEAM SUMMARY
Team | Total Members | Available | Busy | Overloaded | Avg Availability

## Mobile Development
MOBILE DEVELOPMENT - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
MOB001 | iOS Login Screen | Alice Johnson | High | In Progress | 2024-01-01 | 2024-01-15 | 60% | 25 | 18 |  | UI Design, Implementation, Testing | Need to integrate with auth API
TEAM SUMMARY
Total Tasks:
Completed:
In Progress:
Average Progress:

## Data Science
DATA SCIENCE - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
DS001 | Customer Behavior Analysis | Bob Smith | Medium | Planning | 2024-01-10 | 2024-02-01 | 15% | 40 | 6 |  | Data Collection, Analysis, Report | Waiting for data access
TEAM SUMMARY
Total Tasks:
Completed:
In Progress:
Average Progress:

## Weekly Planning
WEEKLY PLANNING
Week Starting: | 2025-09-17
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Mobile Development | Sprint Planning |  |  |  | Sprint Review
Data Science | Sprint Planning |  |  |  | Sprint Review

## Templates
TEMPLATES & INSTRUCTIONS
HOW TO USE THIS TEAM TASK PLANNER:
1. MASTER DASHBOARD:
- Overview of all teams and projects
- Key metrics and performance indicators
- Automatic calculations from team sheets
2. TEAM ALLOCATION:
- Resource management and availability
- Skills tracking and team member status
- Color-coded availability indicators
3. TEAM SHEETS (Frontend, Backend, DevOps, QA):
- Individual task management for each team
- Progress tracking and status updates
- Dependencies and subtask management
4. WEEKLY PLANNING:
- Week-by-week task scheduling
- Cross-team coordination
- Sprint planning support
COLOR CODING:
- Green: Available/Completed/Low Priority
- Yellow: Busy/In Progress/Medium Priority
- Red: Overloaded/High Priority/Overdue
- Blue: In Progress tasks
- Gray: Not Started tasks
FORMULAS USED:
- Task counts: COUNTA functions
- Progress calculations: AVERAGE and SUM
- Status counting: COUNTIF functions
TO ADD NEW TASKS:
1. Go to appropriate team sheet
2. Add new row with task details
3. Use consistent formatting
4. Update dependencies as needed
TO ADD NEW TEAM MEMBERS:
1. Go to Team Allocation sheet
2. Add new row with member details
3. Update team summary if needed
BEST PRACTICES:
- Update progress weekly
- Review master dashboard regularly
- Use consistent task naming
- Track dependencies carefully
- Update availability status

## UI Design
UI DESIGN - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
UI 001 | Sample Task for UI Design | Team Member | Medium | Not Started | 2025-09-17 | 2025-10-01 | 0% | 10 | 0 |  |  | Add your tasks here