## Master Dashboard
TEAM TASK PLANNER - MASTER DASHBOARD
Last Updated: | 2025-09-17 05:48
Project/Team | Total Tasks | Completed | In Progress | Pending | Overdue | Team Size | Workload %
Frontend Team | 15 | 8 | 4 | 3 | 1 | 5 | 85
Backend Team | 20 | 12 | 5 | 3 | 2 | 6 | 90
DevOps Team | 10 | 6 | 2 | 2 | 1 | 3 | 75
QA Team | 12 | 7 | 3 | 2 | 1 | 4 | 80
KEY METRICS
Total Projects:
Total Tasks:
Overall Progress:
Critical Issues:
Average Team Load:

## Team Allocation
TEAM RESOURCE ALLOCATION
Employee Name | Team | Role | Current Tasks | Hours/Week | Availability % | Skills | Next Available | Status
John Doe | Frontend Team | Senior Developer | 3 | 40 | 90 | React, Angular, Vue | 2024-01-15 | Busy
Jane Smith | Frontend Team | UI Designer | 2 | 35 | 75 | Figma, Sketch, CSS | 2024-01-10 | Available
Bob Johnson | Backend Team | Tech Lead | 4 | 45 | 95 | Python, Java, AWS | 2024-01-20 | Overloaded
Alice Wilson | Backend Team | Developer | 2 | 40 | 70 | Node.js, MongoDB | 2024-01-08 | Available
Mike Brown | DevOps Team | Engineer | 3 | 40 | 85 | Docker, Kubernetes | 2024-01-12 | Busy
Sarah Davis | QA Team | Tester | 2 | 35 | 65 | Selenium, Manual Testing | 2024-01-05 | Available
TEAM SUMMARY
Team | Total Members | Available | Busy | Overloaded | Avg Availability

## Frontend Team
FRONTEND TEAM - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
FE001 | User Login Page | John Doe | High | In Progress | 2024-01-01 | 2024-01-15 | 70% | 20 | 18 |  | Design, Code, Test | Need API integration
FE002 | Dashboard Layout | Jane Smith | Medium | Planning | 2024-01-10 | 2024-01-25 | 10% | 30 | 5 | FE001 |  | Waiting for requirements
FE003 | Mobile Responsive | John Doe | High | Not Started | 2024-01-15 | 2024-02-01 | 0% | 25 | 0 | FE002
TEAM SUMMARY
Total Tasks:
Completed:
In Progress:
Average Progress:

## Backend Team
BACKEND TEAM - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
BE001 | User Authentication API | Bob Johnson | High | Completed | 2023-12-15 | 2024-01-05 | 100% | 15 | 16 |  | Design, Code, Test | Ready for frontend
BE002 | Database Schema | Alice Wilson | High | In Progress | 2024-01-01 | 2024-01-12 | 80% | 20 | 18 |  |  | Almost done
BE003 | Payment Gateway | Bob Johnson | Medium | Planning | 2024-01-15 | 2024-02-15 | 5% | 40 | 2 | BE002 |  | Waiting for approval
TEAM SUMMARY
Total Tasks:
Completed:
In Progress:
Average Progress:

## DevOps Team
DEVOPS TEAM - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
DO001 | CI/CD Pipeline | Mike Brown | High | In Progress | 2024-01-01 | 2024-01-20 | 60% | 25 | 20 |  | Setup, Test, Deploy | Docker issues
DO002 | AWS Infrastructure | Mike Brown | Medium | Planning | 2024-01-15 | 2024-02-01 | 20% | 30 | 8 | DO001 |  | Cost optimization needed
DO003 | Monitoring Setup | Mike Brown | Low | Not Started | 2024-02-01 | 2024-02-15 | 0% | 15 | 0 | DO002
TEAM SUMMARY
Total Tasks:
Completed:
In Progress:
Average Progress:

## QA Team
QA TEAM - TASK MANAGEMENT
Week of: 2025-09-17
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Hours Est. | Hours Actual | Dependencies | Subtasks | Notes
QA001 | Login Testing | Sarah Davis | High | In Progress | 2024-01-05 | 2024-01-18 | 75% | 12 | 10 | FE001 | Manual, Auto | Found 2 bugs
QA002 | API Testing | Sarah Davis | High | Not Started | 2024-01-08 | 2024-01-22 | 0% | 15 | 0 | BE001 |  | Waiting for documentation
QA003 | Performance Testing | Sarah Davis | Medium | Planning | 2024-01-20 | 2024-02-05 | 10% | 20 | 2 |  |  | Need test data
TEAM SUMMARY
Total Tasks:
Completed:
In Progress:
Average Progress:

## Weekly Planning
WEEKLY PLANNING
Week Starting: | 2025-09-17
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Frontend Team | Sprint Planning |  |  |  | Sprint Review
Backend Team | Sprint Planning |  |  |  | Sprint Review
DevOps Team | Sprint Planning |  |  |  | Sprint Review
QA Team | Sprint Planning |  |  |  | Sprint Review

## Templates
TEMPLATES & INSTRUCTIONS
HOW TO USE THIS TEAM TASK PLANNER:
1. MASTER DASHBOARD:
- Overview of all teams and projects
- Key metrics and performance indicators
- Automatic calculations from team sheets
2. TEAM ALLOCATION:
- Resource management and availability
- Skills tracking and team member status
- Color-coded availability indicators
3. TEAM SHEETS (Frontend, Backend, DevOps, QA):
- Individual task management for each team
- Progress tracking and status updates
- Dependencies and subtask management
4. WEEKLY PLANNING:
- Week-by-week task scheduling
- Cross-team coordination
- Sprint planning support
COLOR CODING:
- Green: Available/Completed/Low Priority
- Yellow: Busy/In Progress/Medium Priority
- Red: Overloaded/High Priority/Overdue
- Blue: In Progress tasks
- Gray: Not Started tasks
FORMULAS USED:
- Task counts: COUNTA functions
- Progress calculations: AVERAGE and SUM
- Status counting: COUNTIF functions
TO ADD NEW TASKS:
1. Go to appropriate team sheet
2. Add new row with task details
3. Use consistent formatting
4. Update dependencies as needed
TO ADD NEW TEAM MEMBERS:
1. Go to Team Allocation sheet
2. Add new row with member details
3. Update team summary if needed
BEST PRACTICES:
- Update progress weekly
- Review master dashboard regularly
- Use consistent task naming
- Track dependencies carefully
- Update availability status